## Estimate Summary (hidden)
Project Estimate |  | Project Name
Estimate (hours) |  |  | Team (members) | Duration (days) | Estimated cost ($)
Design phase | #REF! | #REF! | #REF! |  | #REF!
Development & deployment |  | #REF! | #REF! | 35 | #REF!
Unit tests | None
Dedicated PM | No
Project management | None | #REF! | #REF! |  | #REF!
Business analysis | None | #REF! | #REF! |  | #REF!
QA | None | #REF! | #REF! |  | #REF!
Total |  | #REF! | #REF! | 35 | #REF!
See 'Project Estimate' worksheet for detailed estimate
Platforms/Technologies
| Technology |  |  |  | Database
Backend | PHP / WordPress |  |  |  | MySQL
Fontend
Assumptions
Items not included to the estimate
Risks |  |  |  |  | Probability | Impact
Risk: Time that will be required for content migration is not clear.

## Ballpark Tasks Estimate
# | Task | Min (man/hrs) | Median (man/hrs) | Max (man/hrs) | Expected (man/hrs) |  | Spent time (hrs) |  |  | Comments | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Investigation phase
| Subtotal: | 0 | 0 | 0 | 0 |  | 0
Development
| [S1] SQL injection exposure in auth and DB access | 6 | 7 | 8 | 8 |  | 0 |  |  | (and possibly write tests that evidence sql injections are fixed) | 0
| [S2] URL-based auto-login bypass | 6 | 8 | 12 | 10 |  | 0 |  |  | Testing is problemtic without live server and clear testing scenarious where auto-login links are actually used | 0
| Prepare & send updated code & report | 2 | 3 | 4 | 4 |  | 0 |  |  |  | 0
| Communication \ risks padding | 4 | 6 | 8 | 7 |  | 0 |  |  |  | 0
[7 empty] | 0 |  |  |  | 0
[7 empty] | 0 |  |  |  | 0
0
| Subtotal: | 18 | 24 | 32 | 29 |  | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| [S3] Weak password hashing | 8 | 10 | 14 | 12 |  | 0 |  |  | Implement automatic hash updates | 0
| [S4] Weak session configuration | 6 | 8 | 10 | 9 |  | 0 |  |  |  | 0
| [S5] Missing session rotation and CSRF protection | 10 | 13 | 16 | 15 |  | 0 |  |  |  | 0
| Communication \ risks padding | 6 | 8 | 10 | 9 |  | 0 |  |  | Since the final testing process is not defined, we cannot be sure of how that can be done | 0
| Subtotal: | 30 | 39 | 50 | 45 | 0 | 0 | 0 | #DIV/0!
Project Total: |  | 48 | 63 | 82 | 74 |  | 0

## Copy of Salary Database Task v2 (hidden)
# | Task | Min (man/hrs) | Median (man/hrs) | Max (man/hrs) | Expected (man/hrs) | Spent time (hrs) | Comments
Investigation phase
| Subtotal: | 0 | 0 | 0 | 0 | 0
Development
Preparations
| Install and review new dumps | 0.5 | 1 | 1 | 1 | 1
| Review, clarofy & discuss task requirements | 3 | 4 | 5 | 5 | 4
Backend
| Create data structure & Salary Database Page | 5 | 7 | 8 | 8 | 12.5 | 3.4 CMS Backend Section ("Gehaltseinträge")
| Update Page - add block | 1 | 1 | 1 | 1 |  | 3.1 Salary Database Page (Entry Type: "Gehaltsdatenbank")
| new CMS block type "Gehaltsdatenbank" | 2 | 3 | 3 | 3 |  | 3.2 Salary Database Table (CMS Block Type "Gehaltsdatenbank-Tabelle")
Import
| import fileds mapping | 1 | 2 | 2 | 2 | 1.5
| Import-script for legacy salary CSV with mapping to new datamodel | 4 | 5 | 8 | 6 |  | Import-script for legacy salary CSV with mapping to new datamodel, de-duplicate where needed, adjust values
| Any legacy entries where a German federal state was mistakenly entered in the “Land” field must be corrected (i.e. set Country = Germany and populate the “Bundesland” field accordingly) | 1 | 1 | 1 | 1
| New entry page | [5 empty] | 3.3 Salary Database Submission Form (Entry Type: "Neuer Gehalts-Eintrag")
| Calrify columns\fields | 2 | 3 | 3 | 3 | 3 | Review & calrify columns, check import data
| Create page and review other form implenations | 2 | 3 | 3 | 3
| Implement and test all fileds | 5 | 6 | 6 | 6
| Conditional logic - The field "Bundesland" (state) should only be visible once "Land" (country) is set to Germany. | 1 | 2 | 2 | 2
| Conditional logic - A toggle ("monthly" ↔ "annual") | 5 | 6 | 8 | 7 | 8 | New toggle field implentation? annual bonus (hidden for internships). (Go over fields file and make sure all conditional logic is implemented)
Frontend
| Display frontend table | 3 | 4 | 4 | 4 |  | Frontend table (filters, sorting, search, pagination)
| Implement and show calculated fileds | 2 | 3 | 3 | 3 |  | normalized full-time annual salary must be recalculated automatically on save.
| Frontend filters and sorts | 3 | 4 | 4 | 4 |  | Assumption: hidden columns are always hidden (but filterable)
| Federal State / Province is filterable only in combination with "Land" | 1 | 1 | 1 | 1
| right-aligning numeric fields | 0.5 | 0.5 | 0.5 | 1
Honeypot
| Carify task requirements and existing implementations | 2 | 3 | 3 | 3 | 2.5 | Review existing functionality and new requirements
| Create ○ new CMS section "Datenbank-Honeypots" | 2 | 2 | 3 | 2 |  | ○ new CMS section "Datenbank-Honeypots"
| Create ○ new block type "Datenbank-Honeypot" | 1 | 2 | 2 | 2 |  | ○ new block type "Datenbank-Honeypot"
| Display honeypot | 2 | 3 | 4 | 4 |  | ○ login-based replacement of the table block for non-logged-in users
| Add translations into file | 1 | 2 | 2 | 2
| Create deploy instrucitons | 1 | 2 | 2 | 2 |  | Documentation of manual steps for deployment (see directory „release-notes“)
Out of scope
| Data visualization with Datawrapper | [5 empty] | out of scope
| Dynamic charts that react to filters | [5 empty] | out of scope
| Communication Padding | 6 | 8 | 8 | 8 | 0.5 | email communication, show & tell meeting, sync reqiredments
| Adjust commits and send final update | 1 | 1 | 2 | 1
| Subtotal: | 58 | 79.5 | 89.5 | 85 | 33
Project Total: |  | 58 | 79.5 | 89.5 | 85 | 33

## Checkpoints (hidden)
| Min | Mid | Max | Load
PM / Development | #REF! | #REF! | #REF! | #REF!
PM daily load (%) | #REF! | #REF! | #REF! | #REF!
PM daily load (hrs) | #REF! | #REF! | #REF! | #REF!

## Lists (hidden)
QA complexity |  |  | Web backend technologies | Web frontend technologies | Hybrid technologies | iOs technologies | Android technologies | Windows application | Databases
Extra | 75% |  | C# / .NET Core | Javascript/Angular | Javascript/ReactNative | Swift/iOs SDK | Kotlin/Android SDK | WPF | MsSQL
High | 50% |  | PHP / Symfony | Javascript/React | Dart/Flutter | ReactNative | ReactNative | WinForms | MySQL
Normal | 35% |  | PHP / WordPress | Javascript/Vue |  | Flutter | Flutter |  | SqLite
Low | 20% |  | PHP / Craft CMS | Javascript/NodeJS |  |  |  |  | Postgresql
None | 0% |  | Java / Spring | Javascript/Jquery |  |  |  |  | Mongodb
Python / Django
Unit Test coverage |  |  | Python / Flask
High | 50% | >50% | Go /Echo
Normal | 30% | 40%-50%
Low | 15% | <40%
None | 0%
Project Management complexity |  |  | Cost calculation | Hourly rate
High | 20% |  | dev | 0
Normal | 12.5% |  | pm | 0
Low | 8% |  | qa | 0
None | 0% |  | ba | 0
BA during development complexity
Fulltime | 100% | 8h/d
High | 50% | 4h/d
Normal | 25% | 2h/d
Low | 12% | 1h/d
None | 0%
Duration
DEV communication | 8%
QA communication | 6%
team
Temp values - don’t edit |  |  |  | Dev | #REF! | #REF! | #REF! | #REF! | #REF! | ndev
QA complexity | 0 |  |  | add dev | #REF! | #REF! | #REF! |  | #REF! | nqa
BA during development % | 0 | [7 empty] | #REF! | total
UnitTests | 0 |  |  | QA | #REF! | #REF! | #REF!
PM % | 0 |  |  | add qa | #REF! | #REF! | #REF!

## Duration (hidden)
Project duration = BA phase duration + (DEV main phase + DEV bugfix + Deployment)
BA phase
Design
BA on support
DEV main phase
DEV bugfix
PM
QA
DEPLOYMENT