## Estimate Summary (hidden)
Project Estimate |  | Project Name
Estimate (hours) |  |  | Team (members) | Duration (days) | Estimated cost ($)
Design phase | #REF! | #REF! | #REF! |  | #REF!
Development & deployment |  | #REF! | #REF! | 35 | #REF!
Unit tests | None
Dedicated PM | No
Project management | None | #REF! | #REF! |  | #REF!
Business analysis | None | #REF! | #REF! |  | #REF!
QA | None | #REF! | #REF! |  | #REF!
Total |  | #REF! | #REF! | 35 | #REF!
See 'Project Estimate' worksheet for detailed estimate
Platforms/Technologies
| Technology |  |  |  | Database
Backend | PHP / WordPress |  |  |  | MySQL
Fontend
Assumptions
Items not included to the estimate
Risks |  |  |  |  | Probability | Impact
Risk: Time that will be required for content migration is not clear.

## 8.5 Upgrade - Deploy and Test
# |  | Task | Min (man/hrs) | Median (man/hrs) | Max (man/hrs) | Expected (man/hrs) | Spent time (hrs) | Comments \ Assumptions | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aug
[29 empty] | 14 | 13 | 12 | 11 | 10 | 9
Investigation phase
|  | Subtotal: | 0 | 0 | 0 | 0 | 0
Development
|  | Test the update and debug locally |  |  |  |  | 0 |  | 0
| Kimi | Franz provides Option A (try first): 2022 database dump |  |  |  |  | 0 |  | 0
| Innowise | Check locally old 8.0 system works with 2022 database data | 4 | 5 | 6 | 6 | 0 | - Install\reinstantialte local 8.0 environemnt - Apply 2022 the dump and check functionality - check test users - run savety net tests - Go over the test scenarios - fix possible dump issues | 0 | [22 empty] | 1
| Kimi | Kimi provides the updated code databse | 0 | 0 | 0 | 0
| Innowise | Checks if the code changes require any updates in the codebase | 1 | 2 | 3 | 3
| Innowise | Apply locally 2022 database data to new 8.5 codebase | 3 | 4 | 6 | 5 |  | - Install\reinstantialte local 8.0 environemnt - Apply 2022 the dump and check functionality - check test users - run savety net tests - fix savety net issues (if any)
| Innowise | Test scenarious | 3 | 4 | 5 | 5 |  | Go over 13 test scenarious
| Innowise | Bugfixing | 4 | 8 | 14 | 11 |  | RISKS: - don't expect big bugs since it's working system being upgraded form PHP 8.0 to 8.5, but risk still exists regarding - not sure how many communicaton may be required to fix the issue (inculde bugfixes for possible bugs that may appear after deployment to test server)
Pessimistic scenario if we need to test
Deploy to test server
| Anexia | Anexia setups test server (Debian 13, PHP 8.5, Copied PHP code from the old production server) | 0 | 0 | 0 | 0 | 0 |  | 0
| Kimi | KImi provides VPN access and access to the new test server | 0 | 0 | 0 | 0
| Innowise | Check VPN & SSH access to test server, make sure all works fine | 2 | 3 | 4 | 4
| Innowise | Deploy to the test server | 2 | 3 | 4 | 4 | 0 | Risk: problems with an access and rights, | 0
| Innowise | Test scenarious | 2 | 3 | 4 | 4 |  | - Go over 13 test scenarious
| Kimi | Checks that all works ok on the test server | 0 | 0 | 0 | 0
| Innowise | Communication padding | 4.2 | 6.4 | 9.2 | 8
[7 empty] | 0 |  | 0
0
|  | Subtotal: | 25.2 | 38.4 | 55.2 | 50 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | If 2022 dump does not suit |  |  |  |  | 0 |  | 0
| Kimi | Franz provides Option B (try first): 2026 stripped production dump |  |  |  |  | 0 | If the 2022 data causes too many problems during testing, you will provide a stripped production dump | 0
| Innowise | Check locally old 8.0 system works with 2026 stripped production dump | 2 | 3 | 3 | 3 |  | OPTIONAL
| Innowise | Apply locally 2026 stripped production dump to new 8.5 codebase | 2 | 3 | 3 | 3 |  | OPTIONAL
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
|  | Subtotal: | 4 | 6 | 6 | 6 | 0
Project Total: |  |  | 29.2 | 44.4 | 61.2 | 56 | 0

## Ballpark Tasks Estimate
# | Task | Min (man/hrs) | Median (man/hrs) | Max (man/hrs) | Expected (man/hrs) |  | Spent time (hrs) |  |  | Comments | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Investigation phase
| Subtotal: | 0 | 0 | 0 | 0 |  | 0
Development
| [S1] SQL injection exposure in auth and DB access | 6 | 7 | 8 | 8 |  | 0 |  |  | (and possibly write tests that evidence sql injections are fixed) | 0
| [S2] URL-based auto-login bypass | 6 | 8 | 12 | 10 |  | 0 |  |  | Testing is problemtic without live server and clear testing scenarious where auto-login links are actually used | 0
| Prepare & send updated code & report | 2 | 3 | 4 | 4 |  | 0 |  |  |  | 0
| Communication \ risks padding | 4 | 6 | 8 | 7 |  | 0 |  |  |  | 0
[7 empty] | 0 |  |  |  | 0
[7 empty] | 0 |  |  |  | 0
0
| Subtotal: | 18 | 24 | 32 | 29 |  | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| [S3] Weak password hashing | 8 | 10 | 14 | 12 |  | 0 |  |  | Implement automatic hash updates | 0
| [S4] Weak session configuration | 6 | 8 | 10 | 9 |  | 0 |  |  |  | 0
| [S5] Missing session rotation and CSRF protection | 10 | 13 | 16 | 15 |  | 0 |  |  |  | 0
| Communication \ risks padding | 6 | 8 | 10 | 9 |  | 0 |  |  | Since the final testing process is not defined, we cannot be sure of how that can be done | 0
| Subtotal: | 30 | 39 | 50 | 45 | 0 | 0 | 0 | #DIV/0!
Project Total: |  | 48 | 63 | 82 | 74 |  | 0

## Copy of Salary Database Task v2 (hidden)
# | Task | Min (man/hrs) | Median (man/hrs) | Max (man/hrs) | Expected (man/hrs) | Spent time (hrs) | Comments
Investigation phase
| Subtotal: | 0 | 0 | 0 | 0 | 0
Development
Preparations
| Install and review new dumps | 0.5 | 1 | 1 | 1 | 1
| Review, clarofy & discuss task requirements | 3 | 4 | 5 | 5 | 4
Backend
| Create data structure & Salary Database Page | 5 | 7 | 8 | 8 | 12.5 | 3.4 CMS Backend Section ("Gehaltseinträge")
| Update Page - add block | 1 | 1 | 1 | 1 |  | 3.1 Salary Database Page (Entry Type: "Gehaltsdatenbank")
| new CMS block type "Gehaltsdatenbank" | 2 | 3 | 3 | 3 |  | 3.2 Salary Database Table (CMS Block Type "Gehaltsdatenbank-Tabelle")
Import
| import fileds mapping | 1 | 2 | 2 | 2 | 1.5
| Import-script for legacy salary CSV with mapping to new datamodel | 4 | 5 | 8 | 6 |  | Import-script for legacy salary CSV with mapping to new datamodel, de-duplicate where needed, adjust values
| Any legacy entries where a German federal state was mistakenly entered in the “Land” field must be corrected (i.e. set Country = Germany and populate the “Bundesland” field accordingly) | 1 | 1 | 1 | 1
| New entry page | [5 empty] | 3.3 Salary Database Submission Form (Entry Type: "Neuer Gehalts-Eintrag")
| Calrify columns\fields | 2 | 3 | 3 | 3 | 3 | Review & calrify columns, check import data
| Create page and review other form implenations | 2 | 3 | 3 | 3
| Implement and test all fileds | 5 | 6 | 6 | 6
| Conditional logic - The field "Bundesland" (state) should only be visible once "Land" (country) is set to Germany. | 1 | 2 | 2 | 2
| Conditional logic - A toggle ("monthly" ↔ "annual") | 5 | 6 | 8 | 7 | 8 | New toggle field implentation? annual bonus (hidden for internships). (Go over fields file and make sure all conditional logic is implemented)
Frontend
| Display frontend table | 3 | 4 | 4 | 4 |  | Frontend table (filters, sorting, search, pagination)
| Implement and show calculated fileds | 2 | 3 | 3 | 3 |  | normalized full-time annual salary must be recalculated automatically on save.
| Frontend filters and sorts | 3 | 4 | 4 | 4 |  | Assumption: hidden columns are always hidden (but filterable)
| Federal State / Province is filterable only in combination with "Land" | 1 | 1 | 1 | 1
| right-aligning numeric fields | 0.5 | 0.5 | 0.5 | 1
Honeypot
| Carify task requirements and existing implementations | 2 | 3 | 3 | 3 | 2.5 | Review existing functionality and new requirements
| Create ○ new CMS section "Datenbank-Honeypots" | 2 | 2 | 3 | 2 |  | ○ new CMS section "Datenbank-Honeypots"
| Create ○ new block type "Datenbank-Honeypot" | 1 | 2 | 2 | 2 |  | ○ new block type "Datenbank-Honeypot"
| Display honeypot | 2 | 3 | 4 | 4 |  | ○ login-based replacement of the table block for non-logged-in users
| Add translations into file | 1 | 2 | 2 | 2
| Create deploy instrucitons | 1 | 2 | 2 | 2 |  | Documentation of manual steps for deployment (see directory „release-notes“)
Out of scope
| Data visualization with Datawrapper | [5 empty] | out of scope
| Dynamic charts that react to filters | [5 empty] | out of scope
| Communication Padding | 6 | 8 | 8 | 8 | 0.5 | email communication, show & tell meeting, sync reqiredments
| Adjust commits and send final update | 1 | 1 | 2 | 1
| Subtotal: | 58 | 79.5 | 89.5 | 85 | 33
Project Total: |  | 58 | 79.5 | 89.5 | 85 | 33

## Checkpoints (hidden)
| Min | Mid | Max | Load
PM / Development | #REF! | #REF! | #REF! | #REF!
PM daily load (%) | #REF! | #REF! | #REF! | #REF!
PM daily load (hrs) | #REF! | #REF! | #REF! | #REF!

## Lists (hidden)
QA complexity |  |  | Web backend technologies | Web frontend technologies | Hybrid technologies | iOs technologies | Android technologies | Windows application | Databases
Extra | 75% |  | C# / .NET Core | Javascript/Angular | Javascript/ReactNative | Swift/iOs SDK | Kotlin/Android SDK | WPF | MsSQL
High | 50% |  | PHP / Symfony | Javascript/React | Dart/Flutter | ReactNative | ReactNative | WinForms | MySQL
Normal | 35% |  | PHP / WordPress | Javascript/Vue |  | Flutter | Flutter |  | SqLite
Low | 20% |  | PHP / Craft CMS | Javascript/NodeJS |  |  |  |  | Postgresql
None | 0% |  | Java / Spring | Javascript/Jquery |  |  |  |  | Mongodb
Python / Django
Unit Test coverage |  |  | Python / Flask
High | 50% | >50% | Go /Echo
Normal | 30% | 40%-50%
Low | 15% | <40%
None | 0%
Project Management complexity |  |  | Cost calculation | Hourly rate
High | 20% |  | dev | 0
Normal | 12.5% |  | pm | 0
Low | 8% |  | qa | 0
None | 0% |  | ba | 0
BA during development complexity
Fulltime | 100% | 8h/d
High | 50% | 4h/d
Normal | 25% | 2h/d
Low | 12% | 1h/d
None | 0%
Duration
DEV communication | 8%
QA communication | 6%
team
Temp values - don’t edit |  |  |  | Dev | #REF! | #REF! | #REF! | #REF! | #REF! | ndev
QA complexity | 0 |  |  | add dev | #REF! | #REF! | #REF! |  | #REF! | nqa
BA during development % | 0 | [7 empty] | #REF! | total
UnitTests | 0 |  |  | QA | #REF! | #REF! | #REF!
PM % | 0 |  |  | add qa | #REF! | #REF! | #REF!

## Duration (hidden)
Project duration = BA phase duration + (DEV main phase + DEV bugfix + Deployment)
BA phase
Design
BA on support
DEV main phase
DEV bugfix
PM
QA
DEPLOYMENT